## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | STUDENT INFORMATION SYSTEM |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | MICKY M. ALMAZORA |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Initiation |  | 2022-12-19 | 2022-12-19 | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter |  | 2022-12-21 | 2022-12-21 | bar: WEEK 2 W
1.2 | Revised Flowchart |  | 2023-01-16 | 2023-01-16 | bar: WEEK 2 W to WEEK 3 W
1.3 | Database structure |  | 2023-01-16 | 2023-01-16 | bar: WEEK 2 R to WEEK 3 R
1.4 | Create Git Repo |  | 2023-01-16 | 2023-01-16 | bar: WEEK 3 M to WEEK 3 R
1.5 | Initial Code | bar: WEEK 3 T to WEEK 3 R
1.6 | bar: WEEK 3 F
2 | Manage Student Information System
2.1 | Login | bar: WEEK 4 M to WEEK 4 R
2.2 | Input username and password | bar: WEEK 4 F to WEEK 5 F
2.3 | Student Information - name,course,section
2.4 | Add records,list,modify,delete,exit program
3 | Project Conception and Initiation
3.1 | Status and Tracking
3.2 | KPIs
3.2.1 | Monitoring
3.2.2 | Forecasts
3.3 | Project Updates
3.3.1 | Chart Updates
4 | Project Performance / Monitoring
4.1 | Project Objectives
4.2 | Quality Deliverables
4.3 | Effort and Cost Tracking
4.4 | Project Performance